## Blad1
Projectnaam | User story # | Work item # | Day 7 - remaining hours | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Sprint 1 | User story 1 | 1.1 Download Pygame | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Make sure you fill in "hours remaining"
Sprint 1 | User story 1 | 1.2 Make Lay-Out | 3 | 1 | 0 | 0 | 0 | 0 | 0
Sprint 1 | User story 1 | 1.3 Put Layout in menu screen | 1 | 1 | 1 | 0 | 0 | 0 | 0
Sprint 1 | User story 2 | 2.1 put a'start' button in menu screen | 3 | 3 | 3 | 2 | 0 | 0 | 0
Sprint 1 | User story 2 | 2.2 put a 'exit' button in menu screen | 2 | 2 | 2 | 2 | 1 | 0 | 0
Sprint 1 | User story 3 | 3.1 put a 'help' button in the menu screen | 2 | 2 | 2 | 2 | 1 | 0 | 0
Sprint 1 | User story 4 | 4.1 create elements on the board | 4 | 4 | 4 | 3 | 2 | 0 | 0
Sprint 1 | User story 4 | 4.2 put all the elements of the board game in the board | 6 | 6 | 6 | 6 | 4 | 1 | 0
Sprint 1 | User story 3 | 6.1 make a pause menu | 2 | 2 | 2 | 2 | 2 | 0 | 0
Sprint 1 | User story 3 | 6.2 put 'exit' button in the pause menu | 2 | 2 | 2 | 2 | 2 | 1 | 0
|  | Ideal | 26 | 22 | 18 | 14 | 9 | 4 | 0
|  | Actual | 26 | 23 | 22 | 19 | 12 | 2 | 0