## PRODUCT BACKLOG
Product Backlog
ID | Feature | Priority | Sprint 1 | Sprint 2 | Sprint 3
1 | Display menu screen on program start. | M | Done
2 | Menu with "Start" and "Exit" buttons. | M | Done
3 | Show the rules of the game when needed by user in the main menu. | M | Done
4 | Display game board in the game. | M | Done
5 | Include boats in the game. | M |  | Done
6 | Include cards in the game. | M |  | To Do
7 | Include actions in the game. | M |  |  | To Do
8 | Display "Exit" button in the pause menu. | M | Done
9 | Display which player is playing the current turn. | M |  | To Do
10 | Execute special actions after getting a card or a special card. | M |  |  | To Do
11 | Change current player after the end of the turn. | M |  | To Do
12 | Show win screen if current player has beaten enemy ships and display winner name. | M |  |  | To Do
13 | "Go back to main menu" button is displayed in the win screen. | S
14 | Current player can pause and resume the game. | S |  | To Do
15 | Produce sound. | C |  |  | To Do
16 | Display moving, attacking, sinking boat animation. | C
17 | Menu extended with "Settings" button (audio volume). | C |  |  | To Do
18 | Possibility to select also computer players. | C
19 | Computer player is able to play the game. | C
20 | Add some humour to the computer player. | W
21 | Save current state of the game on a file. | C
22 | Load a previously saved game state. | C
23 | Make game playable online. | C
24 | Make game playable by users sitting at different PCs (LAN multiplayer). | C

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a user I want to have a main menu so that I can choose the options the game has to offer me. | M | 6 - 12 Hours | - Download Pygame. - Make lay-out. - Put lay-out in menu screen. | - The main menu has to be operateble with all the functions that it must have.
2 | As a user I want a main menu with a "Start" button and an "Exit" button so that I can start or exit the game. | M | 1 - 6 Hours | - Put a "Start" button in menu screen. - Put a "Exit" button in menu screen. | - The "Start" must be operateble. - The "Exit" must be operateble.
3 | As a user I want a "Help" button in the main menu and while I am playing the game so that if I forget a rule I can refer myself to that option. | M | 1 - 6 Hours | - Put a "Help" button in the menu screen. - Put all the rules in it. | - "Help" button must be operateble. - All the rules of the board game must be in it.
4 | As a user I want to have a display of the board in the game so I can familiarise myself with it. | M | 1 - 6 Hours | - Create the elements of the board. - Put all the elements of the board game in the board. | - All the elements of the board game must be in the board.
8 | As user I want to have an "Exit" button in the pause menu so that I can exit the game. | M | 1 - 6 Hours | - Make pause menu. - Put "Exit" button in the pause menu. | - The "Exit" button must be operateble for the pause menu. - The "Exit" button will place the player to the main menu.

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
5 | As a user I want to have boats in the game so that It has "pawns". | M | 1 - 6 Hours | - Create boats. - Put boats in game. | - The boats have their right attributes.
6 | As a user I want to have cards in the game so that it has Special features. | M | 1 - 6 Hours | - Create offensive cards. - Create Defensive cards. - Create "Hulp" cards. - Create Special cards. - Put cards in game. | - All the cards need to have their own unique attributes. - The elements must be correctly displayed.
9 | As a user I want the game to display which player is playing the current turn so that I know who is playing. | M | 1 - 6 Hours | - Make a display of which player's turn it is. - Put display in game | - The display must be shown.
11 | As a user I want the game to change the current player after the end of a turn so that the game will be fair. | M | 1 - 6 Hours | - Create a function "End Turn" that shows which player's turn it is. - Put function in game. | - After the "End Turn" button there must be a display of whose turn it is.
14 | As a user I want the game to be able to pause and resume if the current player wishes to do so, so that the current player can other stuff in the meantime. | S | 1 - 6 Hours | - Program the pause button so that it pauses the game only for the current player. | - The current player must be able to pause the game and not the other player.

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
7 | As a user i want actions in the game so that the game is playable. | M | 1 - 6 Hours | - Create actions in the game. - Put actions in the game. | - The actions are based on the game manual. - The actions are operatable.
10 | As a user I want the game to execute the special actions of a card so that the game is more interesting. | M | 1 - 6 Hours | - Give the playing cards an action after the player triggers a card. - Put special actions in game. | - Each card has their own action. - The cards must be operateble.
12 | As a user I want the game to show the winner after the game so that I know who won. | M | 1 - 6 Hours | - Create a "Victory" screen. - Put "Victory" screen in game. | - There must be a "victory" screen.
15 | As a user I want the game to have sounds so that it is more engaging. | C | 1 - 6 Hours | - Create sound effects. - Put sound effects in game with corresponding actions. | - The sound effects must correspond with their respective actions.
17 | As a user I want a "Settings" option so that I can set the settings of the game to my liking. | C | 1 - 6 Hours | - Create "Settings" button. - Create settings lay-out. - Create audio options. - Put | - Settings must have audio options. - Settings option must be operateble.