## Blad1
Projectnaam | User story # | Work item # | Day 7 - remaining hours | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Sprint 2 | User story 5 | 5.1 Create Boats | 3 | 3 | 2 | 0 | 0 | 0 | 0 | Make sure you fill in "hours remaining"
Sprint 2 | User story 5 | 5.2 Put boats In Game | 3 | 1 | 0 | 0 | 0 | 0 | 0
Sprint 2 | User story 6 | 6.1 Create offensive cards | 1 | 1 | 1 | 0 | 0 | 0 | 0
Sprint 2 | User story 6 | 6.2 Create defensive cards | 3 | 3 | 3 | 2 | 0 | 0 | 0
Sprint 2 | User story 6 | 6.3 Create 'hulp' cards | 2 | 2 | 2 | 2 | 1 | 0 | 0
Sprint 2 | User story 6 | 6.4 Create special cards | 2 | 2 | 2 | 2 | 1 | 0 | 0
Sprint 2 | User story 9 | 9.1 Make a display of which playr's turn it is | 1 | 1 | 0 | 0 | 0 | 0 | 0
Sprint 2 | User story 14 | 14.1 -Program the pause button so that it pauses the game only for the current player. | 4 | 4 | 4 | 4 | 3 | 3 | 2
Sprint 2 | User story 11 | 11.1 Create a function 'End turn' that shows which player's turn it is. | 5 | 5 | 4 | 4 | 3 | 3 | 3
0
|  | Ideal | 24 | 20 | 16 | 12 | 8 | 3 | 0
|  | Actual | 24 | 22 | 18 | 14 | 8 | 6 | 5