## Blad1
Projectnaam | User story # | Work item # | Day 7 - remaining hours | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Sprint 3 | User story 7 | 7.1 Create actions in the game. | 3 | 3 | 2 | 0 | 0 | 0 | 0 | Make sure you fill in "hours remaining"
Sprint 3 | User story 7 | 7.2 - Put actions in the game. | 3 | 1 | 0 | 0 | 0 | 0 | 0
Sprint 3 | User story 12 | 12.1 - Create a 'victory' screen. | 1 | 1 | 1 | 0 | 0 | 0 | 0
Sprint 3 | User story 12 | 12.2 - Put a 'Victory' screen in game. | 3 | 3 | 3 | 2 | 0 | 0 | 0
Sprint 3 | User story 15 | 15.1 - Create sound effects. | 2 | 2 | 2 | 2 | 1 | 0 | 0
Sprint 3 | User story 17 | 17.1 - Create settings button. | 2 | 2 | 2 | 2 | 1 | 0 | 0
Sprint 3 | User story 17 | 17.2 - Create settings layout. | 1 | 1 | 0 | 0 | 0 | 0 | 0
Sprint 3 | User story 17 | 17.3 - Create audio options. | 5 | 5 | 4 | 4 | 3 | 3 | 3
Sprint 3 | User story 17 | 17.4 - Put options in the 'settings'. | 4 | 4 | 4 | 4 | 3 | 3 | 2
0
|  | Ideal | 24 | 20 | 16 | 12 | 8 | 3 | 0
|  | Actual | 24 | 22 | 18 | 14 | 8 | 6 | 5